## Sheet1
dd/mm-dd/mm | Guo: Yuhan (Member 1) | SURNAME : FIRST NAME (Member 2) | SURNAME : FIRST NAME (Member 3)
28/09-30/09 | Work: 1. Project initiation completed. Topic: an offline, single-file revision web app for Cambridge IGCSE Computer Science 0478 (2026-2028 syllabus). Problem: each syllabus objective is only one line, but the exam expects the detail behind it (e.g. a packet = header + payload + trailer). 2. Goals set: cover every syllabus objective, one at a time; explain the implied exam knowledge in notes; stay strictly inside the syllabus; keyboard-first navigation; save revision progress locally; no installation needed. 3. Used AI to help write the first version (HTML/CSS/JavaScript). I set the requirements and reviewed the output. Basic functions are complete: 10 topics, 24 sections, 102 objectives, syllabus sidebar, notes panel, mark-as-reviewed with progress, reset, keyboard shortcuts, dark mode and mobile layout. 4. Next: add more features and improve content quality, then plan the weekly milestones up to the December presentation. Source: - Cambridge International, IGCSE Computer Science 0478 syllabus for 2026-2028 (Version 6): https://www.cambridgeinternational.org/Images/697167-2026-2028-syllabus.pdf - Claude (Anthropic AI assistant): used to help generate the first version of the code and notes. | Work: Source: | Work: Source:
08/10-10/10 | Work: Reviewed the whole revision app against my own revision notes (PDF) and the 0478 2026–2028 syllabus wording. Tested in Chromium: all 102 objectives load with no page errors, and keyboard navigation and the "reviewed" toggle work. Fixed a real bug found during testing: programming/SQL keywords such as FOR, FROM and AND were being highlighted inside ordinary sentences. The matcher now uses whole-word, case-sensitive matching for short keywords. Added about 120 syllabus terms, so notes with fewer than two highlights fell from 52 to 11. Added 16 inline SVG diagrams in the Notes panel (logical shifts, two's complement, storage units, file-size calculation, transmission methods, block parity, compiler vs interpreter, trace table, logic gate symbols, development life cycle, bubble sort, arrays, blockchain, cookies, NIC/router, ASCII table). Replaced the external image with an inline table so the app does not depend on the internet. Added short notes to thin objectives (8.1.1, 8.1.3, 8.1.4, 3.4.1) and a comparison table for error-detection methods (2.2.2). Corrected the packet trailer to "error-check data" using my notes. Removed unused CSS. Source:Cambridge IGCSE Computer Science 0478 (2026–2028) syllabus; my own revision notes (PDF); AI assistance (Claude) for code and diagrams, with me setting requirements and reviewing results. | Work: Source: | Work: Source:
12/10-16/10 | Work: 1. Widened the scope: from one hard-coded syllabus (0478) to any syllabus the user uploads. 2. Chose DeepSeek (OpenAI-compatible API, cheap, Chinese pricing page) and designed a two-step reading process: send the whole text once to locate the content pages and count the objectives of each section, then re-send only those pages in overlapping chunks to copy the objectives word for word. 3. Put "=== PAGE n ===" in front of every page so each objective can be traced back to the page it came from. Source: - Cambridge IGCSE 0610 / 0625 syllabuses as test data; DeepSeek API documentation. - AI assistant for code and prompt wording. | Work: Source: | Work: Source:
19/10-23/10 | Work: 1. Tested the extraction on real syllabuses: single objectives were missed, some numbers appeared twice, and many syllabuses print Core and Supplement as two lists that share one numbering (Core 1-4, then Supplement 5-7). 2. Added a three-way check after every extraction: the count the AI reported, the numbers the app scans from the raw PDF text itself, and the number actually extracted - compared section by section. 3. Added an automatic re-read of the missing numbers instead of asking the user to repair them by hand. Source: - Cambridge IGCSE 0610 / 0625 syllabuses; my notes on the syllabus numbering. - AI assistant for code and prompt wording. | Work: Source: | Work: Source:
26/10-30/10 | Work: 1. Added card generation: highlighted key terms, short notes, and a table or flow diagram where it helps. 2. Generation runs in batches of five, several in parallel, and each finished batch is saved at once, so a run can be stopped and continued later. 3. The AI returns structured data only; the app draws the tables and SVG diagrams itself, so a bad answer cannot break the page. 4. Compact single-line JSON with short keys and a word budget per command word keeps the cost down. Source: - Cambridge IGCSE command words; my own revision notes. - DeepSeek API documentation (JSON mode, cache pricing). | Work: Source: | Work: Source:
02/11-06/11 | Work: 1. Added a recovery stage for objectives still missing after the re-read: the model receives the section, the missing numbers, the objectives already found and the syllabus text of those pages. 2. Three rules in order: copy verbatim if the objective is printed; if the numbering shows a hole, infer one objective in the style of its neighbours and mark it "AI added"; otherwise leave the number out. 3. Added a local safety rule: an inferred number above the highest already found in that section, or a whole section that was never extracted, is discarded. The app never invents an objective the syllabus does not have. Source: - Cambridge IGCSE 0625 / 0620 syllabuses with deliberate gaps. - AI assistant for the code; the rules are mine. | Work: Source: | Work: Source:
09/11-13/11 | Work: 1. Long objectives with (a)(b)(c) sub-points did not fit on one card, so I built pagination. 2. The split is measured, not guessed: a hidden element renders the objective at the real font size and card width, and it is split only above 62% of the card; no page then takes more than 72%. 3. Split points are chosen so the pages end up most even - (a)(b)(c) boundaries first, then semicolons, then words. 4. The card only jumps back to the top when moving to another objective, not when turning a page. Source: - My own revision notes and the 0478 sub-point format. - AI assistant for the code. | Work: Source: | Work: Source:
16/11-20/11 | Work: 1. Built the four-step wizard for adding a subject (name, upload, recognise, generate) with a step bar showing the current step. 2. Changed all prices to CNY, taken from the official DeepSeek pricing page, and applied the off-peak rate outside the weekday peak hours (09:00-12:00 and 14:00-18:00 Beijing time). 3. Step 4 shows an estimated cost range before anything is generated, and the progress bar shows the spend while it runs. Thinking mode is off by default: it costs several times more and a fixed extraction task does not need it. Source: - DeepSeek official pricing page. - AI assistant for the code. | Work: Source: | Work: Source:
23/11-27/11 | Work: 1. By now the whole app was one 428 KB HTML file of about 8,400 lines, including a single 162 KB data line, so I restructured it into 54 pieces: 11 CSS files, 11 markup pieces, 24 JavaScript modules, 6 files for the five AI prompts, and the built-in 0478 data as a JSON file. 2. Wrote build.py to reassemble the pieces, and proved it by rebuilding and comparing byte for byte with the original: the same 428,774 bytes and the same SHA-256, so the restructuring changed nothing in the app. 3. Wrote check.py, run after every edit: the rebuilt file matches the pieces, every element id used by the code exists, brackets and quotes are balanced, serve.py serves the current file, and a headless browser confirms the app still renders. Tested by breaking things on purpose in a copy - it caught all seven cases. Source: - My own project files; Python documentation. - AI assistant for the tooling; the structure is my decision. | Work: Source: | Work: Source:
30/11-04/12 | Work: Source: | Work: Source: | Work: Source:
07/12-11/12 | Work: Source: | Work: Source: | Work: Source:
14/12-18/12 | Work: Source: | Work: Source: | Work: Source:
21/12-25/12 | Work: Source: | Work: Source: | Work: Source:
28/12-31/12 | Work: Source: | Work: Source: | Work: Source: